BOOK MY FIT

Project Plan & Task Breakdown

Full Development Roadmap — Phase 1 through Phase 4

■  PROJECT OVERVIEW

## Phased Delivery Plan

| Phase | Scope | Duration (Est.) | Key Deliverable |
| --- | --- | --- | --- |
| 1 | Foundation: Auth, Gym onboarding, Individual Subscription, QR Check-in | 10 weeks | MVP — Individual gym subscriptions working end-to-end |
| 2 | Elite/Pro Multi-Gym, Settlement Engine, Commission Engine | 8 weeks | Multi-gym platform live; revenue distribution working |
| 3 | PT Add-on, Wellness, Corporate, Store, Videos | 8 weeks | Full marketplace with all revenue streams |
| 4 | Analytics, AI Recommendations, Slot Booking, Scale | 6 weeks | Growth features, optimizations, scale readiness |

PHASE 1 — FOUNDATION & MVP (10 Weeks)

## Epic 1.1: Project Setup & Infrastructure

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-1.1.01 | Initialize React Native (Expo) project with TypeScript | Frontend | 3h | High |
| T-1.1.02 | Configure NativeWind (Tailwind CSS) + global dark theme tokens | Frontend | 4h | High |
| T-1.1.03 | Set up Redux Toolkit + RTK Query store architecture | Frontend | 6h | High |
| T-1.1.04 | Configure React Navigation v6: Stack + Tab + Auth navigators | Frontend | 4h | High |
| T-1.1.05 | Initialize Next.js project for Admin + Gym + Wellness portals | Frontend | 4h | High |
| T-1.1.06 | Configure shadcn/ui component library for portals | Frontend | 3h | High |
| T-1.1.07 | Initialize NestJS backend with modular architecture | Backend | 8h | High |
| T-1.1.08 | Set up PostgreSQL with TypeORM; define migration pipeline | Backend | 6h | High |
| T-1.1.09 | Set up Redis for session and daily lock cache | Backend | 4h | High |
| T-1.1.10 | Configure AWS S3 bucket + presigned URL generation service | Backend | 4h | High |
| T-1.1.11 | Set up Razorpay account + webhook endpoint + test keys | Backend | 3h | High |
| T-1.1.12 | Configure Firebase Cloud Messaging for push notifications | Backend | 3h | High |
| T-1.1.13 | Set up CI/CD pipeline (GitHub Actions + EAS Build) | DevOps | 6h | Medium |
| T-1.1.14 | Configure Sentry error monitoring for mobile + backend | DevOps | 3h | Medium |
| T-1.1.15 | Design and implement global glassmorphism design system (BlurCard, GlowButton, NeonInput) | Frontend | 12h | High |

## Epic 1.2: Database Schema Design

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-1.2.01 | Design Users table + indices | Backend | 2h | High |
| T-1.2.02 | Design Gyms + GymDocuments + GymKYCSteps tables | Backend | 4h | High |
| T-1.2.03 | Design Categories + Amenities master tables | Backend | 2h | High |
| T-1.2.04 | Design SubscriptionPlans + Subscriptions tables | Backend | 4h | High |
| T-1.2.05 | Design CheckIns table + daily lock Redis schema | Backend | 3h | High |
| T-1.2.06 | Design CommissionRules table (global + gym-specific) | Backend | 3h | High |
| T-1.2.07 | Design Settlements + Invoices tables | Backend | 4h | High |
| T-1.2.08 | Design PTProfiles + PTBookings tables | Backend | 3h | High |
| T-1.2.09 | Design WellnessServices + WellnessBookings tables | Backend | 3h | High |
| T-1.2.10 | Design Ratings + Reviews tables | Backend | 2h | High |
| T-1.2.11 | Design AuditLogs table | Backend | 2h | Medium |
| T-1.2.12 | Design Products + Orders + OrderItems tables | Backend | 3h | High |
| T-1.2.13 | Write seed data for categories and amenities | Backend | 2h | Medium |

## Epic 1.3: Authentication Module

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-1.3.01 | Implement OTP generation + SMS integration (Twilio/Fast2SMS) | Backend | 4h | High |
| T-1.3.02 | Implement JWT access token + refresh token rotation | Backend | 4h | High |
| T-1.3.03 | Implement role-based guards (Super Admin, Staff, Gym, Wellness, User) | Backend | 4h | High |
| T-1.3.04 | Implement device fingerprint binding on login | Backend | 3h | High |
| T-1.3.05 | Build Splash Screen (mobile) | Frontend | 2h | High |
| T-1.3.06 | Build Onboarding slides (3 screens with Lottie) | Frontend | 6h | High |
| T-1.3.07 | Build Login screen with OTP flow | Frontend | 8h | High |
| T-1.3.08 | Build OTP verification screen with countdown | Frontend | 4h | High |
| T-1.3.09 | Build Google Sign-In integration | Frontend | 4h | Medium |
| T-1.3.10 | Wire auth state to Redux + persisted secure storage | Frontend | 4h | High |

## Epic 1.4: Gym Onboarding & KYC

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-1.4.01 | Build Gym self-registration API (create account, step validation) | Backend | 6h | High |
| T-1.4.02 | Build document upload API (S3 presigned + step tracking) | Backend | 6h | High |
| T-1.4.03 | Build admin KYC review API (approve/reject per step with remarks) | Backend | 4h | High |
| T-1.4.04 | Build gym status lifecycle API | Backend | 2h | High |
| T-1.4.05 | Build Gym Registration portal (multi-step form + doc upload UI) | Frontend (Web) | 16h | High |
| T-1.4.06 | Build KYC Status Tracker page | Frontend (Web) | 6h | High |
| T-1.4.07 | Build Admin KYC Review Panel (step-by-step approve/reject) | Frontend (Web) | 12h | High |
| T-1.4.08 | Send email notification on document rejection with remarks | Backend | 3h | Medium |

## Epic 1.5: Category & Amenities Engine

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-1.5.01 | Build admin CRUD API for categories | Backend | 3h | High |
| T-1.5.02 | Build admin CRUD API for amenities + gym request flow | Backend | 4h | High |
| T-1.5.03 | Build gym category/amenity selection API | Backend | 2h | High |
| T-1.5.04 | Build Category Management page (admin portal) | Frontend (Web) | 6h | High |
| T-1.5.05 | Build Amenities Master page (admin portal) | Frontend (Web) | 6h | High |
| T-1.5.06 | Implement category visibility rule (hide if no active gym mapped) | Backend | 2h | High |

## Epic 1.6: Individual Subscription

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-1.6.01 | Build gym subscription plan CRUD API | Backend | 4h | High |
| T-1.6.02 | Build commission deduction logic on individual subscription purchase | Backend | 6h | High |
| T-1.6.03 | Build subscription purchase API with Razorpay payment initiation | Backend | 6h | High |
| T-1.6.04 | Build Razorpay webhook handler (payment confirmation) | Backend | 4h | High |
| T-1.6.05 | Build subscription activation on payment success | Backend | 3h | High |
| T-1.6.06 | Build Subscription Introduction page (app) | Frontend | 6h | High |
| T-1.6.07 | Build Duration Selection page with PT toggle | Frontend | 8h | High |
| T-1.6.08 | Build Order Summary + Coupon page | Frontend | 6h | High |
| T-1.6.09 | Build Payment flow (Razorpay SDK integration) | Frontend | 6h | High |
| T-1.6.10 | Build Payment Success screen | Frontend | 4h | High |
| T-1.6.11 | Build My Subscriptions page | Frontend | 6h | High |
| T-1.6.12 | Build Gym Subscription Plans management page (gym portal) | Frontend (Web) | 8h | High |

## Epic 1.7: QR Check-In System

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-1.7.01 | Implement dynamic QR token generation (HMAC-SHA256, 30s expiry) | Backend | 6h | High |
| T-1.7.02 | Implement QR validation API (8-step access control sequence) | Backend | 10h | High |
| T-1.7.03 | Implement Redis daily lock (userId:date key write/check) | Backend | 4h | High |
| T-1.7.04 | Implement check-in attendance logging | Backend | 2h | High |
| T-1.7.05 | Build QR Generation screen (animated countdown ring, auto-refresh) | Frontend | 10h | High |
| T-1.7.06 | Build Check-In Result screen (success / fail states with animation) | Frontend | 4h | High |
| T-1.7.07 | Build Check-In History page (app) | Frontend | 4h | Medium |
| T-1.7.08 | Build QR Scanner screen (gym portal — camera view + result display) | Frontend (Web) | 8h | High |
| T-1.7.09 | Build Check-In Logs page (gym portal) | Frontend (Web) | 6h | High |

## Epic 1.8: User App Core UI

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-1.8.01 | Build Home Dashboard screen | Frontend | 12h | High |
| T-1.8.02 | Build Category Listing screen | Frontend | 4h | High |
| T-1.8.03 | Build Gym Listing screen (with filters + map toggle) | Frontend | 12h | High |
| T-1.8.04 | Build Gym Details screen (tabs: Overview, Services, Trainers, Reviews) | Frontend | 16h | High |
| T-1.8.05 | Build User Profile screen | Frontend | 6h | High |
| T-1.8.06 | Implement geo-location + nearest gym sorting | Frontend + Backend | 6h | High |
| T-1.8.07 | Build Notifications screen | Frontend | 4h | Medium |
| T-1.8.08 | Build Gym Dashboard home screen (gym portal) | Frontend (Web) | 10h | High |
| T-1.8.09 | Build Edit Gym Profile page (gym portal) | Frontend (Web) | 8h | High |

## Epic 1.9: Admin Core Panel

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-1.9.01 | Build Admin Login with 2FA | Frontend (Web) | 6h | High |
| T-1.9.02 | Build Super Admin Dashboard (KPIs + charts) | Frontend (Web) | 12h | High |
| T-1.9.03 | Build User Management page | Frontend (Web) | 8h | High |
| T-1.9.04 | Build Gym Management page (list + status filter) | Frontend (Web) | 8h | High |
| T-1.9.05 | Build Commission Engine page (global + per-gym overrides) | Frontend (Web) | 10h | High |
| T-1.9.06 | Build Audit Logs page | Frontend (Web) | 6h | Medium |

■  PHASE 2 — ELITE/PRO + SETTLEMENT ENGINE (8 Weeks)

## Epic 2.1: Elite & Pro Subscription Engine

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-2.1.01 | Build Elite/Pro plan CRUD API (admin controlled) | Backend | 4h | High |
| T-2.1.02 | Implement Elite pool collection on subscription purchase | Backend | 4h | High |
| T-2.1.03 | Implement Pro pool collection (separate bucket) | Backend | 3h | High |
| T-2.1.04 | Extend QR validation to support Elite/Pro gym tier checks | Backend | 6h | High |
| T-2.1.05 | Build Elite/Pro plan builder UI (admin portal) | Frontend (Web) | 10h | High |
| T-2.1.06 | Build multi-gym subscription purchase flow (app) | Frontend | 10h | High |
| T-2.1.07 | Display Elite/Pro eligible gyms separately in discovery | Frontend | 4h | High |

## Epic 2.2: Gym Tier Classification

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-2.2.01 | Build gym tier assignment API (admin) | Backend | 3h | High |
| T-2.2.02 | Apply Pro pool tier multiplier logic (Standard 1x, Premium 1.5x) | Backend | 4h | High |
| T-2.2.03 | Build Gym Tier Assignment page (admin portal) | Frontend (Web) | 6h | High |
| T-2.2.04 | Show tier badge on gym cards in user app | Frontend | 2h | Medium |

## Epic 2.3: Settlement Engine

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-2.3.01 | Build revenue bucket tracking service (per subscription type) | Backend | 8h | High |
| T-2.3.02 | Build visit-ratio calculation service for Elite pool distribution | Backend | 8h | High |
| T-2.3.03 | Build weighted visit-ratio service for Pro pool (with tier multiplier) | Backend | 6h | High |
| T-2.3.04 | Build monthly settlement calculation cron job | Backend | 6h | High |
| T-2.3.05 | Build invoice generation service (PDF via pdfkit) | Backend | 4h | High |
| T-2.3.06 | Build invoice approval + payout status tracking API | Backend | 4h | High |
| T-2.3.07 | Build Settlement Dashboard page (admin portal) | Frontend (Web) | 14h | High |
| T-2.3.08 | Build Earnings Dashboard page (gym portal) | Frontend (Web) | 10h | High |
| T-2.3.09 | Build Settlement Report + Raise Invoice page (gym portal) | Frontend (Web) | 8h | High |
| T-2.3.10 | Build breakage profit tracking (unused subscription value) | Backend | 4h | Medium |

## Epic 2.4: Rating & Review System

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-2.4.01 | Build rating submission API (gym, PT, wellness) with eligibility check | Backend | 4h | High |
| T-2.4.02 | Build admin rating moderation API (approve/reject) | Backend | 3h | High |
| T-2.4.03 | Implement rating impact on gym tier eligibility logic | Backend | 3h | Medium |
| T-2.4.04 | Build Rate & Review bottom sheet (mobile app) | Frontend | 6h | High |
| T-2.4.05 | Build Reviews tab in Gym Details page | Frontend | 6h | High |
| T-2.4.06 | Build Ratings Moderation page (admin portal) | Frontend (Web) | 6h | Medium |

## Epic 2.5: Fraud Prevention & Security

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-2.5.01 | Implement duplicate scan detection (idempotency key in Redis) | Backend | 3h | High |
| T-2.5.02 | Implement suspicious activity flagging (velocity check) | Backend | 6h | High |
| T-2.5.03 | Implement device mismatch fraud alert | Backend | 4h | High |
| T-2.5.04 | Build Fraud Monitoring page (admin portal) | Frontend (Web) | 8h | High |
| T-2.5.05 | Implement screenshot blur on QR screen (iOS/Android) | Frontend | 4h | High |

■  PHASE 3 — FULL MARKETPLACE (8 Weeks)

## Epic 3.1: PT Add-On Module

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-3.1.01 | Build PT profile CRUD API (gym portal) | Backend | 4h | High |
| T-3.1.02 | Build PT booking API + commission deduction | Backend | 6h | High |
| T-3.1.03 | Build PT settlement bucket + tracking | Backend | 3h | High |
| T-3.1.04 | Build PT Management page (gym portal) | Frontend (Web) | 10h | High |
| T-3.1.05 | Integrate PT selection in subscription purchase flow (app) | Frontend | 8h | High |
| T-3.1.06 | Build PT booking standalone page (from gym details) | Frontend | 6h | High |
| T-3.1.07 | Build Trainers tab in Gym Details screen | Frontend | 4h | High |

## Epic 3.2: Wellness Services

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-3.2.01 | Build Wellness Partner registration + KYC (similar to gym) | Backend | 8h | High |
| T-3.2.02 | Build Wellness service CRUD + booking API | Backend | 6h | High |
| T-3.2.03 | Build Wellness commission + settlement tracking | Backend | 4h | High |
| T-3.2.04 | Build Wellness Partner portal pages (service mgmt, bookings, settlement) | Frontend (Web) | 20h | High |
| T-3.2.05 | Build Wellness discovery in user app (category + listing + booking) | Frontend | 12h | High |
| T-3.2.06 | Build Wellness Partner Management page (admin portal) | Frontend (Web) | 8h | High |

## Epic 3.3: Corporate Subscriptions

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-3.3.01 | Build Corporate Account creation API | Backend | 4h | High |
| T-3.3.02 | Build bulk seat assignment + employee onboarding API | Backend | 8h | High |
| T-3.3.03 | Build corporate settlement tracking (under Elite/Pro pool) | Backend | 4h | High |
| T-3.3.04 | Build Corporate Accounts management page (admin portal) | Frontend (Web) | 12h | High |
| T-3.3.05 | Build Corporate dashboard for HR admin (seat usage, employees) | Frontend (Web) | 12h | High |

## Epic 3.4: E-Commerce Store

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-3.4.01 | Build product CRUD API (admin only) | Backend | 6h | High |
| T-3.4.02 | Build order creation + payment API | Backend | 6h | High |
| T-3.4.03 | Build order management + refund API | Backend | 4h | High |
| T-3.4.04 | Build Store Management pages (admin portal: products, orders, refunds) | Frontend (Web) | 16h | High |
| T-3.4.05 | Build Store tab in mobile app (category, product grid, detail) | Frontend | 14h | High |
| T-3.4.06 | Build Cart + Checkout + Order History (mobile app) | Frontend | 10h | High |

## Epic 3.5: Workout Videos

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-3.5.01 | Build video upload API + S3 storage (admin) | Backend | 4h | High |
| T-3.5.02 | Build video access control (free vs premium gating) | Backend | 3h | High |
| T-3.5.03 | Build Video Management page (admin portal) | Frontend (Web) | 8h | High |
| T-3.5.04 | Build Workout Videos screen + video player (mobile app) | Frontend | 10h | High |

## Epic 3.6: Push Notifications + Coupons

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-3.6.01 | Build subscription expiry notification cron job | Backend | 3h | Medium |
| T-3.6.02 | Build PT/wellness booking confirmation notifications | Backend | 2h | Medium |
| T-3.6.03 | Build admin manual push notification API | Backend | 3h | Medium |
| T-3.6.04 | Build Notification Panel page (admin portal) | Frontend (Web) | 6h | Medium |
| T-3.6.05 | Build Coupon Engine API (create, validate, apply) | Backend | 6h | Medium |
| T-3.6.06 | Build Coupon Management page (admin portal) | Frontend (Web) | 6h | Medium |

■  PHASE 4 — GROWTH & SCALE (6 Weeks)

## Phase 4 Tasks

| Task ID | Task Description | Area | Est. | Priority |
| --- | --- | --- | --- | --- |
| T-4.01 | Build analytics dashboard (admin): peak hours, churn, visit trends, revenue by category | Backend + Frontend | 16h | High |
| T-4.02 | Implement gym capacity live counter (real-time via WebSocket) | Backend + Frontend | 10h | Medium |
| T-4.03 | Build slot booking system (book class time at gym) | Backend + Frontend | 20h | Medium |
| T-4.04 | Implement AI recommendation engine (nearest + category preference + history) | Backend | 16h | Medium |
| T-4.05 | Build membership freeze feature (pause subscription for N days) | Backend + Frontend | 8h | Medium |
| T-4.06 | Build referral system (refer a friend for discount) | Backend + Frontend | 10h | Medium |
| T-4.07 | Build loyalty point system (check-ins = points = rewards) | Backend + Frontend | 12h | Medium |
| T-4.08 | Performance optimization: Redis caching layer for gym listings | Backend | 8h | High |
| T-4.09 | Implement database query optimization + read replicas | DevOps | 10h | High |
| T-4.10 | Load testing (k6) — simulate 10,000 concurrent QR validations | QA / DevOps | 8h | High |
| T-4.11 | Penetration testing — auth, QR bypass attempts, API security | Security | 16h | High |
| T-4.12 | Build city-based pricing admin configuration | Backend + Frontend | 6h | Low |
| T-4.13 | App Store + Play Store submission preparation (screenshots, metadata, compliance) | Frontend | 8h | High |
| T-4.14 | GDPR / data privacy audit + compliance implementation | Backend | 8h | High |
| T-4.15 | GST invoice generation for all payment types | Backend | 6h | High |

■  PROJECT SUMMARY & TEAM STRUCTURE

## Recommended Team Composition

| Role | Count | Responsibility |
| --- | --- | --- |
| React Native Developer | 2 | Mobile app — all user-facing screens + Redux + navigation |
| Next.js / React Web Developer | 1-2 | Admin panel + Gym portal + Wellness portal |
| NestJS Backend Developer | 2 | All APIs, business logic, settlement engine, QR system |
| UI/UX Designer | 1 | Figma designs — glassmorphism dark theme system |
| DevOps / Cloud Engineer | 1 | AWS infra, CI/CD, Redis, DB, monitoring |
| QA Engineer | 1 | Manual + automated testing; QR system; payment flows |
| Product Manager | 1 | Sprint planning, stakeholder communication, feature prioritization |

## Total Estimated Timeline

| Phase | Duration | Cumulative | Key Milestone |
| --- | --- | --- | --- |
| Phase 1 | 10 weeks | 10 weeks | MVP live: individual gym subscriptions + QR check-in |
| Phase 2 | 8 weeks | 18 weeks | Multi-gym platform live; settlement engine running |
| Phase 3 | 8 weeks | 26 weeks | Full marketplace: PT, wellness, store, corporate, videos |
| Phase 4 | 6 weeks | 32 weeks | Scale-ready: analytics, AI, slot booking, App Store live |
| TOTAL | ~32 weeks | ~8 months | Production-ready enterprise platform |